## Pragati CR5 Audit
S No | Audit Concerns | Comments | Project | Status
1 | Have you asked QA to add more AC thought by yourself to this list? (you will know more than the QA because you are writing the code) | Concerns from QA Team: Devs not asking additional UACs and they don’t update us on the coverage | Pragati CR5
2 | Do you know the names of the resources (entities or tables) to which data will be written and which columns/rows will be written? | Good to have for QA. | Pragati CR5
3 | is there an ER Diagram that explains the table relationships? | We have ERD for only few modules | Pragati CR5
4 | While Story grooming, MM also need to explain on a high level along with each stories | Need to take care during story grooming session | Pragati CR5
5 | Need to introduce a little technical aspect in the story gromming session for API Request/Response | Tech Spec & AC both should be there | Pragati CR5 | Need to setup a meeting UI members
6 | API Design including End Point/Request/Response structure must be finalized before we do Story Gromming session | This need to highlighted in the API Matrix or in some other document (MoM)/Change log and need to communicated with team as well properly. | Pragati CR5
7 | Story Grooming is not planned on Tuesday, it is happening on someother day | This has been taken care | Pragati CR5
8 | Team should have approved wireframes before Story Gromming session | This will keep coming again & again. | Pragati CR5
9 | Require API documentation with versioning | Concerns from DEV Team: No visibility of changes in the API | Pragati CR5
10 | UI design references create a confusion. Which reference to follow like Zeplin or Figma. | Recommendations: There should be one URL for each story/screen pointing out the specific screen that is being referred. | Pragati CR5
11 | There should be some sort of annotation on Figma regarding design changes as it's expected that changes might not reflect frequently on Zeplin. | In DGA, we have asked BA & ES Team to highlight the issues in the wireframes by doing Annotations in the PDF generated from Figma and share the same to rest of the team as well. | Pragati CR5
12 | Frequent changes into wireframes once development starts | Quite similar to Point no 8 | Pragati CR5

## DGA CR2 Audit
S No | Audit Concerns | Comments | Project
1 | Wireframes from Pragati application are not placed at one place in some cases, which makes it difficult to find sometimes i.e. training module | Training module was completely reused in the DGA CR2 from Pragati | DGA CR2
2 | Need to provide UJ & related AC's to developers during Story Gromming sessions | Good to have: UJ should also be part of Story Grooming and has to be developed by ES team | DGA CR2
3 | QA should add AC's related to data validaions, drop down dependencies & Page validations | Data validations more need to enhanced | DGA CR2
5 | Good to have the HiFi designs also | Good to have | DGA CR2
6 | Postman collection will help better for development, if present | Will create Postman collection. Should be part of GIT | DGA CR2
7 | QA Team should be familiar with the MM | Need to check with team about the MM Understanding | DGA CR2
8 | Need to provide OData training for the new members | https://www.odata.org/getting-started/ https://services.odata.org/v4/northwind/northwind.svc/ | DGA CR2
9 | Girish will prepare a document which will summarize the API calling mechanism & different use cases in case of POST/PUT, so that we can save development efforts | Document has been created and shared with the API Team | DGA CR2
10 | Estimations was not properly done, specially where we need to copy/paste code from Pragati | Learning: This has to be taken care from next time onwards specially where we have to copy code from another application | DGA CR2
11 | Only knowledgeble person of code should do the copy/paste activity, then it should handover to developers | Learning: This has to be taken care from next time onwards specially where we have to copy code from another application | DGA CR2
12 | Basic functional knowledge of existing module, should be there for all before coding |  | DGA CR2
13 | Story Matrix is not complete for Traning module (Need to check for other missing stories) |  | DGA CR2
14 | Multiple things at the same time, difficult to manage for developers i.e. CR1 bug fixing, development or something else | Avoid context switching | DGA CR2
15 | Design Feedback should be given by BA in PDF by annotate & add comments. Should be shared with everyone in the team including ES | Both has to be in sync | DGA CR2
16 | No Nasty surprises at the last moment, better to have desing confirmation before development |  | DGA CR2
17 | Delay in API readiness while doing UI development | Avoid context switching | DGA CR2
18 | Backlog - Define a dedicated time slot in days to close it. Delay the project milestone by one week | Because of context switching | DGA CR2
19 | Weekly deliverables are not provided to QA on time for testing | Because of context switching | DGA CR2
20 | As a best practice, all the questions & answers discussed with customer must be placed in a document and should be date wise |  | DGA CR2