## Questions
Question | Yes/No
Can you identify rows in WBS that represents your allocated work in THIS week?
Can you identify the Page Names and Story Names from the WBS?
Do you know how to find out the wireframes associated with your tasks?
Do you know how to find out related hi-fi design?
If you do not find the wireframe or hi-fi design, how will you find out?
Do you know how to find out related stories in the MM? - and the page context?
Do you know the context of User Journey for the story?
Do you know how to find Acceptance Criteria related to your Story or Page or UJ?
Do you know what are the page validation rules, drop-down dependencies?
Do you know what are the data related AC? (storage, retrieval, aggregation, sorting, row filtering…)
Have you asked QA to add more AC to this list? (you will know more than the QA because you are writing the code)
Will the UI of your story call single aggregate API or multiple individual resource APIs? (both GET and POST - relevant to your task)
Do you know what are the request/response parameters?
Do you know the names of the resources (entities or tables) from which data will be fetched and which columns/rows will be filtered?
Do you know the names of the resources (entities or tables) to which data will be written and which columns/rows will be written?
is there an ER Diagram that explains the table relationships?
Do you know which 3rd party (example: ECC) apis need to be called? Their Request/Response pairs?
Do you know who (programmers) are dependent on you?
Do you know on whom you depend?
Do you see any technical risks that are yet unresolved?
Can this audit list be improved with additional questions? (especially related to testing of the business rules)
Can this audit list be improved by changing wording of some questions?
Have you written a "specifications" document? If yes, does it answer all the above questions?
Do you know the process of verification of stories with QA, before you deliver build it to them?
Do you know about the GIT branching strategy?
Do you know about the CI/CD or deployment process?

## DGA Audit Report - Week1
S No | Title
1 | Wireframes from Pragati application are not placed at one place in some cases, which makes it difficult to find sometimes i.e. training module
2 | Need to provide UJ & related AC's to developers during Story Gromming sessions | UJ will created by ES Team
3 | QA should add AC's related to data validaions, drop down dependencies & Page validations | Data validations more need to enhanced
4 | Need to provide the SQL basic training for developers/QA | HLD/LLD Sessions
5 | Good to have the HiFi designs also | Need to explain team with appropriate examples
6 | Postman collection will help better for development, if present | Will create Postman collection. Should be part of GIT
7 | QA Team should be familiar with the MM | Need to check with team about the MM Understanding
8 | Need to provide OData training for the new members | North wind url | https://www.odata.org/getting-started/ https://services.odata.org/v4/northwind/northwind.svc/
9 | Girish will prepare a document which will summarize the API calling mechanism & different use cases in case of POST/PUT, so that we can save development efforts

## DGA Audit Report - Week2
1 | Estimations was not properly done, specially where we need to copy/paste code from Pragati | Sameer | JAVA
2 | Only knowledgeble person of code should do the copy/paste activity, then it should handover to developers | Sameer | JAVA
3 | Basic functional knowledge of existing module, should be there for all before coding | Sameer | JAVA
4 | Story Matrix is not complete for Traning module (Need to check for other missing stories) | Ashish | JAVA
5 | Multiple things at the same time, difficult to manage for developers i.e. CR1 bug fixing, development or something else | Pratik | JAVA | Define the Priority is more important to avoid context switch
6 | Design Feedback should be given by BA in PDF by annotate & add comments. Should be shared with everyone in the team including ES | Mamta | UI5
7 | No Nasty surprises at the last moment, better to have desing confirmation before development | Mamta | UI5
8 | Delay in API readiness while doing UI development | Mamta | UI5
9 | Backlog - Define a dedicated time slot in days to close it. Delay the project milestone by one week | Akhil | UI5
10 | Weekly deliverables are not provided to QA on time for testing | Sachin | QA
11 | As a best practice, all the questions & answers discussed with customer must be placed in a document and should be date wise | Nilesh | BA

## Pragati Audit Report - Week1
Correct way to indentify the wireframes through WBS & Story matrix using Story name & page name. No email exchanges should happed with screen shots internally.
Need to check, if Design Studio providing the wire frames in the correct sequence ?
Wireframe has to present in a common folder, shared among all
While Story grooming, MM also need to explain on a high level along with each stories
QA should provide url of AC to every one in the team
Need to introduce a little technical aspect in the story gromming session for API Request/Response
API Design including End Point/Request/Response structure must be finalized before we do Story Gromming session